| **Title** | **Zoom Meeting of Morale Project Work packages Strategies** | **Date** | **26 January 2021** |
| --- | --- | --- | --- |
| **Place** | **Virtual** | **Time** | **2:00 pm Beirut Time** |
| **Attendants** | Sobhi Abou Shahin(BAU), Mayssah El Nayyal(BAU), Abdul Rahman Beydoun (BAU), Rana Hatab(BAU), Bassem EL Kaissi(MUBS), Selim Mekdessi(LU), Marie Aboujaoude(LU), Sarah Makhoul (LU); Sulaiman Mouselli (AIU), Chafdi Azmeh (IUST), Mhd Saeed Barazi (Bilad Acham University), Rabih Chattat(UNIBO), Luis Gómez de Membrillera (University of Alicante) , Laura Sadowski | | |

|  |  |
| --- | --- |
|  | Agenda |
| **1** | **Welcoming Remarks:**  Dr sobhi welcomed partners and thanked them for their commitment and attendance of the meeting |
| **2** | **WP3: Capacity Building WP3: Training Plan**   * Dr. Rabih Chattat discussed the proposal regarding the adoption of strategy mentioning it could be shared amongs partners.   It was agreed to:   * Make cross checking by Lebanese and Syrian partners. * The time for training will be for three days from (9:00 am till 3:00 pm). * The number of participants will be according to the proposal * The number of trainees in the training replication training needs to be revised. |
| **3** | **WP 4: Curricula enhancement & delivery : Strategy for Curricula Modernization**  Dr. Luis Gómez discussed the proposal and he focused mainly on the Curricula enhancement and delivery, needs analysis conclusions, strategy and steps, marketing plan, evaluation.  It was agreed to:  - Enroll at least 25 students according to the capacity of each HEI.  - Ensure that 30% of the modernised course will be delivered in according to partners’ capacities  - Start implementation in the Spring semester of the academic year 2021/2022. |
| **4** | **WP 5: LLL Courses Design & Implementation : Strategy for Lifelong Learning (LLL) Courses**  Dr. Bassem Kaissi discussed the proposal and he focused mainly on the Strategy Objective, LLL Definition, Recommended LLL Courses/Topics, Recommended Instructional Methods for the LLL Online Part, Recommended Blended Learning Structure for the LLL Courses, Final Assessment and evaluation  The recommended timetable was adopted:   |  |  | | --- | --- | | February 10, 2021: | Selection of 3 LLL course titles from each PC HE | | April 10, 2021: | 3 LLL courses completed by each PC HEI | | April 30, 2021: | 3 LLL courses marketing campaign completed by each PC HEI | | May 15, 2021 – continuing: | 3 LLL courses delivery and implementation at each PC HEI. | |
| **5** | **WP 1: Management Issues**  In the framework of finalization of the mid-term report, the grant coordinator urged the partners to send the staff cost documents, answering the external evaluator questionnaires and the mid-term report questions. |

|  |  |
| --- | --- |
|  |  |